## Sheet1
WBS Number | Task Name | WBS Description | Must start by date | Must end by date | No. of Hours | No. of Days | Resources | Author of item
1 | Plan the travel information | The website will need a description of the train schedules and the stations they will stop at. | 2023-03-10 | 2023-04-20 | 50 | 40 | Various websites and travel agents | Rumman
1.1 | Develop database structure | Make a variety of tables with the prices and schedules for the various trains. | 2023-03-25 | 2023-03-31 | 10 | 6 | MySQL and Microsoft Excel | Gaurav
1.2 | Load data into database | By using any web server, create a database online, and enter the aforementioned information into the appropriate tables. | 2023-04-01 | 2023-04-20 | 20 | 20 | Any backend programing language like PHP | Ketki
1.2.1 | Build train catalogue | Include accessible locations together with their costs and estimated travel times. | 2023-04-01 | 2023-04-20 | 20 | 20 | MySQL Queries | Goerge
1.2.1.1 | Identify destination train station | Study of locations of railroad stations at potential destinations | 2023-04-01 | 2023-04-10 | 5 | 10 | Any search engine like Google | Harshit
1.2.1.2 | Contact person at ticket counter | Establish a network of individuals at the ticket counter to offer the ticket's various details. | 2023-04-11 | 2023-04-20 | 10 | 9 | A mode of commutation to visit them | Priyansh
1.2.1.3 | Sign collaborations | Deals on signs that guarantee a profit margin to the ticket counter employee while also keeping prices low for the clients | 2023-04-21 | 2023-05-29 | 5 | 8 | Agreements | Kruthik
1.3 | Sign agreement with banks | To facilitate online payments, sign agreements with banks and various government agencies. | 2023-04-25 | 2023-05-10 | 20 | 15 | Agreements | Izhan
1.3.1 | Sign legal papers with banks | Make agreements with multiple banks, including Axis Bank, HDFC Bank, and others, to handle customer payments | 2023-04-25 | 2023-04-28 | 5 | 3 | Agreements | Salman
1.3.2 | Get permission from income tax department | Obtain approval from the income tax authorities to enable card and even UPI online payments | 2023-03-01 | 2023-03-10 | 15 | 10 |  | Vishal
2 | Purchase Infrastructure | includes purchasing several items to verify the functionality | 2023-03-30 | 2023-04-20 | 15 | 21 | Suffecient investment | Pranav
2.1 | Purchase Hardware | Purchase a workspace and desks for employees so they may help clients and handle inquiries. | 2023-03-30 | 2023-04-05 | 10 | 6 | Labour force and office space | Pranav
2.2 | Purchase Software | Purchase a variety of servers, a hosting service for the website, and specialised tools for website customization. | 2023-04-06 | 2023-04-20 | 5 | 14 | Websites to buy the respective tools | Pranav
3 | Develop website | The last stage of website creation and posting work | 2023-04-21 | 2023-05-30 | 69 | 39 | Web developers and respective laguages | Guhan
3.1 | Design interface | Make a paper version of the website's design that will be used. | 2023-04-21 | 2023-05-01 | 40 | 10 | Web designers/ UX designers | Guhan
3.2 | Build web interface | Create the foundational elements of the website and its features. | 2023-05-02 | 2023-05-15 | 10 | 13 | HTML, CSS, Javascript | Pranav
3.3 | Test web interface | Use a few dummy users to test the website and collect feedback. | 2023-05-16 | 2023-05-24 | 10 | s |  | Guhan
3.4 | Deploy web interface | Make the necessary modifications, then publish the website online. | 2023-05-25 | 2023-05-30 | 9 | 5 | Server | Pranav